## Slide 1: What decision must leadership make?
1 | THE EXECUTIVE DILEMMA
HRHS Enterprise AI: From Strategic Decision to Engineering Execution | Fictional Healthcare Technology Advisory Case Study
THE OPPORTUNITY
THE CONSTRAINT
$640M
annual supply spend; on-contract est. 71% vs 85% target
$38M
annual denial write-offs; 30% to 50% assumed preventable
11 + 2
proposed AI use cases, plus two pilots running without enterprise review
92%
of FY2027 discretionary IT capacity already committed
6,800
uncommitted hours vs ~14,000 needed for a governed first phase
4,600
specialist hours needed are committed to the ERP and EHR programs
vs
The decision (Dec 9, 2026, scenario): How should HRHS approach enterprise AI, and what can it actually commit to in FY2027, given that approving a strategy does not create engineering capacity?
Notes: TALKING POINTS - Fictional case: a six-hospital regional system, 1.2% margin. All data are simulated; I built this to show method, not a real engagement. - Left side is the pull: real money in supply chain and denials, and departments already moving on AI. - Right side is the brake: capacity is 92% committed, and the constraint is specialist skills, not total hours. - The decision is two-part: the approach, and what we can genuinely commit to. ASSUMPTIONS TO NAME IF ASKED - $4.5M provisional envelope (A-01); 30-50% preventable denials (A-03); on-contract 71% (A-02). LIKELY CHALLENGE - "Why not just buy a tool?" That is Option A, and it is legitimate; slide 3. REFERENCES: HRHS-AI-01 Issue Brief; HRHS-AI-02 F-01, F-04, F-08. TRANSITION: Before choosing, separate what we know from what we are assuming.

## Slide 2: What do we know, assume, and need to validate?
2 | WHAT THE EVIDENCE SUPPORTS
Finding | Simulated evidence [S] | Implication | Validation status | Decision consequence
Governance is absent (F-05) | No AI inventory, risk tiering, or evaluation; P-02 ran 5 months with no success measure | Value and risk cannot be compared across 11 proposals | High within case | Minimum governance needed under any option
Unresolved PHI vendor risk (F-04) | P-01 vendor data-use terms unreviewed; contract auto-renews Jan 31 | HIPAA applies; no violation identified, but terms must be verified before renewal | Confirm by Day 30 (V-04) | Act now regardless of option (D-04)
Data readiness is uneven (F-02) | 18% of item-master records incomplete; 23% of denials coded "other" | Supply chain usable with remediation; clinical data is not | Validate Days 30 to 60 (V-02, V-03) | Start in supply chain; sequence UC-02
Specialist capacity is binding (F-08) | 6,800 of 85,000 hours free; 4,600 specialist hours committed to ERP/EHR | Approval does not create capacity | Validate Days 15 to 20 (V-05) | Recommendation conditional on validated capacity (D-05)
Read with care: every finding is simulated within a fictional case. In a real engagement, each would be validated (V-01 to V-07) before money or people are committed. Estimates are plus or minus 30%.
Notes: TALKING POINTS - Four findings drive the decision; the rest of the assessment is supporting detail. - Two are "act now" items regardless of strategy: governance and P-01's patient-data terms. Note the precision: the P-01 finding is an unresolved vendor risk, not a confirmed violation. Nobody has reviewed the terms; that is exactly why it is urgent before the January 31 renewal. - Data readiness tells us where to start (supply chain) and why to sequence UC-02. - The capacity finding is the one that turns a strategy into a commitment question. ASSUMPTIONS - Status column separates simulated certainty from what a real organization would still need to prove. LIKELY CHALLENGE - "How confident are you?" Confident in the logic; the numbers are simulated and every one has a validation owner and date. REFERENCES: HRHS-AI-02 readiness matrix and capacity table; HRHS-AI-03 V-01 to V-07. TRANSITION: Given this evidence, three paths are credible.

## Slide 3: Which alternative best serves the organization?
3 | THREE CREDIBLE PATHS FORWARD
A
Targeted, Vendor-Led
+
Fastest value (4 to 6 months); lowest 3-year cost
−
Controls applied product by product; vendor dependency
Capacity
9,000 IT hours (~1,200 specialist)
Exposure
$2.55M FY27 | $6.35M 3-yr
Weighted score 3.43
B
Governed, Phased
Provisional recommendation
+
Reusable controls and shared capabilities lower cost of later use cases
−
~$1.4M more than A over 3 years; needs specialist release
Capacity
14,000 IT hours (4,600 specialist)
Exposure
$3.75M FY27 | $7.75M 3-yr
Weighted score 3.52
C
Platform-First
+
Strongest long-term foundation
−
Value deferred to 2028; exceeds envelope
Capacity
30,000 IT hours (~11,000 specialist)
Exposure
$7.9M FY27 | $12.3M 3-yr
Weighted score 2.51
The recommendation changes if: HRHS has no pipeline beyond Wave 1, or weights speed over control (A wins); specialist capacity cannot be validated (reduced B, else A); capacity is freed and 15+ use cases are committed (C). All options meet the same mandatory controls; the 0.09 gap is within judgment error.
Notes: TALKING POINTS - All three are legitimate. A is not the "cheap wrong answer"; on three-year quantified financials it is about $1.4M cheaper than B. - Every option has to meet the same privacy, security, and contractual obligations. That floor is not what separates them. - B is provisionally preferred for what it adds beyond the floor: reusable controls, consistent risk evaluation, shared technical capabilities, less duplication across later use cases. - That premium is only worth paying if there is a real pipeline and the specialists can be released. - C is the best foundation but asks for capacity HRHS does not have and defers value into 2028. ANALYTICAL ASSUMPTIONS - Eleven weighted criteria; ratings are judgments. I re-rated A twice against my own earlier work: on cost (A is cheapest over three years) and on safety (A meets the same mandatory controls, so the gap is assurance consistency, one point, not two). B's lead fell from 0.31 to 0.09. - Sensitivity: about 3 weight points from safety to speed flips it to A; with no pipeline beyond Wave 1, A wins outright. - Low-case benefits do not repay any option within three years. That is stated, not hidden. LIKELY CHALLENGES - "Aren't you just protecting B?" No: I re-rated it down myself, and I show the exact conditions that make A right. - "Benefits?" UC-02 $0.45M to $1.1M per year; denials $1.0M to $3.4M net, low confidence. REFERENCES: HRHS-AI-03 scoring, sensitivity, three-year view; HRHS-AI-04. TRANSITION: Even the right strategy fails if the organization cannot deliver it. This is where it gets real.

## Slide 4: Can the organization actually deliver the decision?
4 | THE ENGINEERING REALITY
1 THE CONSTRAINT
1,700
specialist hours unavailable when Wave 1 needs them (Days 1 to 120)
Needed
2,600
Available
900
Hours exist in aggregate (14,000 planned). The skills and the delivery window do not: ERP conversion and EHR cutover hold the same specialists. Found in validation on Day 18 and escalated the same day.
2 THE ALTERNATIVES
1
Sequence Wave 1
UC-01 now, UC-02 after ERP go-live: savings arrive ~4 months later
2
Reallocate engineering capacity
Holds the AI schedule, but puts the ERP go-live at risk
3
Purchase or source externally
Adds ~$0.35M and cannot start before ~Day 75
3 THE DECISION
Sequence Wave 1 now. Obtain vendor pricing for a Day 60 decision. Reallocate ERP capacity only after written confirmation of acceptable impact.
Notes: TALKING POINTS (aim for under two minutes) - Hypothetical: leadership provisionally picked B. On Day 15 engineering managers submitted named allocations, which met the prerequisite. Validation against the ERP and EHR release calendars is where it broke: on Day 17 the ERP program updated its conversion plan, and on Day 18 I reconciled the plans and found 1,700 of 2,600 specialist hours unavailable in the window. I logged it and told the sponsor and CIO the same day, and held Wave 1 spend. - Capacity has four states: planned, provisionally committed, validated, available in window. Plans fail when they treat the first two as the last. - Three ways out. Option 1 is within Steering authority, reversible, and protects both go-lives, so I recommend it now and price option 3 in parallel for a Day 60 decision. - I would not move ERP capacity without the ERP program confirming in writing that go-live is unaffected. That decision belongs to the ERP sponsor, not to me. SUPPORTING DETAIL (HRHS-AI-08) - Specialist hours, Days 1 to 120 (needed / available): ERP item-master 1,400 / 400; integration 600 / 300; security architecture 300 / 0; enterprise architecture 300 / 200. - Wave 1 critical path: provisional allocation Day 15 > validation Day 20 > item-master remediation Days 31 to 58 > UC-02 acceptance criteria Day 60 > G3 ~Day 65. The AI gateway is off this path because Wave 1 uses no patient data; SIEM onboarding (DP-06) is planned for month 6. - Conflicts: ERP phase 2 conversion to go-live ~Day 120 (freeze from Day 90); EHR cutover holds the security architect to month 5. - Costs: option 1 neutral (~$0.2M of FY2027 spend shifts later; ~$0.1M to $0.25M less UC-02 savings in FY2027); option 2 neutral to AI budget, ERP impact needs a quote; option 3 +$0.35M one-time, +$0.12M per year from the $0.75M contingency. - Authority: option 1 Steering Committee; option 2 ERP executive sponsor with CIO/CTO, ELT if a go-live moves; option 3 CFO with VP Supply Chain and CIO/CTO for architecture. - Inputs due before Day 30: ERP impact assessment (Day 25), written release dates (Day 25), restated benefits (Day 28), vendor quotes (Day 45). LIKELY CHALLENGES - "Why not push engineering harder?" Compressing gates during release windows moves risk into ERP and EHR cutovers. - "Doesn't this weaken Day 90 evidence?" Yes. UC-01 has no direct monetized benefit, so G4 also weighs P-02 and a restated case. If nothing works by Day 60, the conditions for Option A are met and I would say so. TRANSITION: Once decided, how will leadership know it is working?

## Slide 5: How will leadership know whether execution is working?
5 | DECISION TO MEASURABLE OUTCOMES
Day 0
G0 Authorize
ELT
Days 15 / 20
Capacity allocated, then validated
CIO/CTO + TPM
Day 30
G1 Governance baseline
Steering
Day 60
G2 Design and readiness
Steering + CISO
~Day 65
G3 Pilot go/no-go
Risk Board + product owner
Day 90
G4 Scale, revise, or stop
CFO + ELT
Delivery readiness (G3)
Acceptance criteria approved
Controls MC-01 to MC-06 evidenced
Support runbook and rollback
Pilot users trained
Business value
On-contract spend vs 71% baseline
Output acceptance rate
Net denial recovery collected
Finance-validated, never summed
Escalation thresholds
Capacity unavailable in window: 1 day
Gate at risk > 2 weeks
Variance > 10% or $100K
Patient-data incident: 24 hours
Proceed: criteria met, controls conform
Pivot: evidence favors Option A
Slow: capacity short: sequence scope
Stop: criteria unmet after one revision
AI informs. Humans decide. Leaders own.
Notes: TALKING POINTS - Six checkpoints in 90 days, each with a named decision owner. The Day 15 to 20 capacity check (allocate, then validate against ERP/EHR calendars) is the one most plans skip, and in this case it is where the conflict surfaced. - Production is not promised by Day 90. A G3 no-go is a valid outcome. - Value is measured against Finance-confirmed baselines; savings, revenue recovery, and risk reduction are reported separately. - Escalation thresholds are agreed up front, so escalating is routine, not personal. - Four outcomes at every gate: proceed, pivot, slow, or stop. Pivot includes switching to Option A if the evidence says so. ASSUMPTIONS - Tranche 2 ($2.25M) released only at G4 on evidence; contingency $0.75M held by CFO. LIKELY CHALLENGES - "Isn't this a lot of governance?" One monthly steering meeting on gate days, a biweekly risk board for higher-risk uses only, and a 30-minute weekly dependency review. - "Who is accountable?" Business owners own value, engineering managers own delivery and estimates, I own the integrated plan and the honesty of the reporting. REFERENCES: HRHS-AI-06 gates; HRHS-AI-07 scorecard and thresholds; HRHS-AI-09 (prep only). TRANSITION TO DISCUSSION (in your own words) The phased approach is my provisional recommendation, but it depends on leadership's investment priorities and engineering's ability to commit the necessary resources. If those conditions change, the recommendation should change with them. My responsibility is to make the tradeoffs visible and make sure the selected direction is executable. Then invite challenge: "Where would you push back? I'm happy to walk through the case for Option A, or what happens if the ERP sponsor says no."